## Slide 1: Integration Management

## Slide 2: Agenda
Introduction
Integration management processes & Process groups
Definitions
Integration management processes
  Inputs, Tools & techniques and Outputs
Wrap up

## Slide 3: Managing Integration - Introduction
What is managing Integration? Why needed?
Do you have a proper project plan?
Are the other management plans included in the project plan
Do you have a proper change control mechanism?
Do you have scheduled status review meetings?
Do you maintain the information on deliverables?
Do you have project baselines?
What is product scope?
What is project scope?

## Slide 4: Managing Integration - Introduction
Project is planned by moving down the list
  Scope : What needs to be done
  Quality : Product performance standards
  Time : The time and sequential order of tasks
  Cost : How much will the task/project cost
  Risk : What is the degree of uncertainty
  Quality : Human performance standards
  HR : Type of people required
  Procurement : Commitments to be procured
  Communication : How will all these people communicate together
Project is controlled by moving up the list

## Slide 5: Integration Management
Project Integration Management is the function required to ensure that the various elements of the project are properly coordinated.
Project Integration
  “The bringing together of diverse organizations, groups or parts to form a cohesive whole to successfully achieve PROJECT OBJECTIVES.”
  “Process to bring different elements together to meet or exceed stakeholders expectations.”

## Slide 6: Integration Management processes (Process groups)
Initiating
None
Planning
Project Plan Development
Executing
Project Plan Execution
Controlling
Integrated Change Control
Closeout
NONE

## Slide 7: Integration Management Processes
Project Plan Development
Integrating and coordinating all project plans to create a consistent, coherent document
Project Plan Execution
Carrying out the project plan by performing the activities included therein
Integrated Change Control
Coordinating changes across the entire project

## Slide 8: Definitions
Project Management Software -
Is a tool that aids integration within a project
Control Account Plans (CAP) -
All the defined, planned, estimated, scheduled and authorized work with the use of detailed integrated management control plan
Total Project Scope -
Sum of all the integrated management control plans will constitute the total project scope

## Slide 9: Project Plan Development
Taking the results of other planning processes and putting them into a consistent, coherent document
An iterative process to achieve a coherent document
Serves to guide project execution
Documents project planning assumptions
Documents decisions
Facilitates communication
Provides a baseline for progress measurement and control

## Slide 10: Project Plan Development
INPUT
Tools &
Techniques
Output
Project Planning Methodology
Stakeholder skills and knowledge
Project Management Information System (PMIS)
Earned Value Management (EVM)
Project Plan
Supporting Details
Other Planning Outputs
Historical Information
Organizational Policies
Constraints
Assumptions

## Slide 11: Project Plan
Project Plan
- A formal, approved document used to manage project execution.
- Otherwise known as integrated project plan
- A document or collection of documents that should be expected to
change over time as more information becomes available about the
project
Project Plan includes
  Project Charter
  Project Management approach or strategy
  Project Objectives / Project Deliverables
  Work Breakdown Structure
  Scope Management Plan
  Schedule Management Plan
  Cost Management Plan
  Risk response plan
  Staffing Management Plan

## Slide 12: Project Plan Execution
Is the actual performance of all project activities
Carrying out the project plan
The vast majority of the project cost will be expanded in performing the execution process
Managing the technical and organizational project interfaces

## Slide 13: Project Plan Execution
Project Plan
Supporting details
Organizational Policies
Preventive Action
Corrective Action
INPUT
Tools &
Techniques
Output
General Management Skills
Product Skills and Knowledge
Work Authorization System
Status Review Meetings
Project Management Information System
Organizational Procedures
Work Results
Change Requests

## Slide 14: Work Authorization System
  A formal procedure for sanctioning project work to ensure that work is done at the right time and in proper sequence
  The design of the system should balance the value of the control provided with the cost of that control.

## Slide 15: Work Results
Outcomes of the activities performed to accomplish the project.
Can be tangible or intangible
It Includes
  Project justification
  Project’s product
  Project deliverables
  Project Objectives

## Slide 16: Change Requests
Change requests (e.g. to expand or contract project scope, to modify cost (budgets), or schedule estimates are often identified while the work of the project is being done
Change requests can occur in many forms - oral or written, direct or indirect, externally or internally initiated, and legally mandated or optional

## Slide 17: Integrated Change Control
Coordinates changes across the entire project
Concerned with influencing the factors which create changes
Ensures that the changes are beneficial
Determine that a change has occurred
Managing the actual changes when and as they occur
Maintains the integrity of any performance measurement baseline
Ensures that changes are reflected in the scope definition and product specifications
Coordinates changes across all knowledge areas

## Slide 18: Integrated Change Control
Project Plan
Performance reports
Change requests
INPUT
Tools &
Techniques
Output
Change Control Systems
Configuration Management
Performance Measurement
Additional planning
PM Information System
Project Plan updates
Corrective action
Lessons Learned

## Slide 19: Change Control System
A collection of formal, documented procedures that defines how project performance will be monitored and evaluated
Includes the paperwork, tracking systems, processes, and approval levels necessary for authorizing changes

## Slide 20: Elements of a Change Control System
Capture and record change requests/proposals
Agreed on Definition of priority classification
  Mandatory, Critical, Value Added, Preferential
Classification process of change request/proposal
Impact evaluation and quantification
Agreed on Review/approval/decision process
Process of information update and communication
Implementation planning

## Slide 21: Configuration Management
A documented procedure used to apply technical and administrative direction and surveillance to
  Identify and document the functional and physical characteristics of an item or system
  Control any changes to such characteristics
  Record and report the change and its implementation status
  Audit the items and system to verify conformance to requirements

## Slide 22: Project Management Information Systems
It consists of tools and techniques used to gather, integrate, and disseminate the outputs of project management processes.
It is used to support all aspects of the project from initiating through closing and can include both manual and automated systems

## Slide 23: Integration Management Wrap-up
Integration Management Processes
Definitions
Project Plan
Work results
Change Control Systems

## Slide 24: Thank you Q & A