## Slide 1: Time Management

## Slide 2: Contents
Introduction
Time management
  Processes
  Concepts
  Definitions

## Slide 3: Introduction
Project Time Management is all about ensuring timely completion of the project
  Define activities by decomposing the the scope
  Identify dependencies among activities
  Estimate individual activities
  Develop a project schedule
  Track & control changes to the schedule

## Slide 4: Introduction (Process groups)
Initiating
NONE
Planning
Activity Definition
Activity Sequencing
Activity Duration Estimates
Schedule Development
Executing
NONE
Controlling
Schedule Control
Closeout
NONE

## Slide 5: Activity Definition
Input process
WBS
Scope Statement
Historical Information
Constraints
Assumptions
Activity list
Support Details
WBS updates
Decomposition
Templates
Output process
Tool
- Identifying and documenting specific activities for producing all deliverable and sub deliverable identified in the WBS

## Slide 6: Activity Sequencing
Activity list
Product description
Dependencies
Constraints
Assumptions
Project Network Diagram
Activity List Updates
PDM
ADM
CDM
Network Template
Input process
Output process
Tool
- Identifying and documenting interactions and dependencies between activities

## Slide 7: Types of Dependencies
Mandatory Dependency
Inherent in the nature of work to be done. Also referred to as Hard Logic
E.g._ Design before you Construct
Discretionary Dependency
Based on experience, desire or performances. Also referred to as Soft logic
E.g._ Code walk through before Testing
External Dependency
Involve a relationship between project activities and non project activities
E.g._ Delivery of h/w before commencement of s/w development

## Slide 8: Network Diagrams
Work packages (lowest level of WBS) are arranged in the order of completion from beginning to end
Two ways of drawing a Network Diagram
Activity A
Activity B
Activity D
Activity
F
Activity
E
A
C
B
D
  AON (Activity on Node). Also called precedence diagramming method (PDM)
  AOA (Activity on Arrow). Also called as Arrow diagramming method (ADM)

## Slide 9: Precedence Diagramming Method
Most Commonly used diagramming method that can depict several Start (S), Finish (F) relationships
FS
FF
SS
SF
with lag SS2

## Slide 10: Arrow Diagramming Method
A
E
B
D
C
F
G
Dummy
Arrows represent tasks & Nodes represent task dependencies
Can depict only Finish to Start relationships
Dummy activities represented by dotted lines are used to show dependencies between tasks

## Slide 11: Conditional Diagramming Method
Facilitates modeling non-sequential activities such as loops & conditional branching
E.g.:
Graphical Evaluation and Review Technique(GERT)
System Dynamics models

## Slide 12: Definitions
Critical Path : Longest Path through a network diagram and determines the earliest completion of the project
Lag : waiting time between two tasks
Slack or Float : Amount of time a task can be delayed without delaying the project
Slack = LS (Latest Start) – ES (Earliest Start)
Slack = LF (Latest Finish) – EF (Earliest Finish)
Discussions:
What is the available slack for tasks in the Critical Path ?
How is Slack Calculated ?
Forward Pass & Backward Pass

## Slide 13: More Definitions ….
Free Float : Amount of time a task can be delayed without delaying the early start date of its successor
Total Float : Amount of time a task can be delayed without delaying the project completion date
Project Float : Amount of time a project can be delayed without delaying the project completion date

## Slide 14: Activity Duration Estimation
Input process
Activity list
Constraints
Assumptions
Resource reqmts
Resource capabilities
Historical Information
Activity Duration Estimates
Basis of Estimate
Activity List Update
Expert Judgment
Analogous Estimating
Simulation
Output process
Tool

## Slide 15: Guidelines for Estimating Duration
Evaluate each activity independently
Assume a normal level of labor and equipment
Assume a normal workday/workweek
Disregard any predetermined contract completion date
use consistent time units
Use past actual duration as guides

## Slide 16: Estimating by Experience
Most Accurate
Based on “Personal” Experience
Must be Adjusted to Reflect Anticipated Environment

## Slide 17: Estimation by Comparison
More accurate than using mathematical formulas
Based on “Someone Else’s “ Experience
Must be adjusted to reflect the anticipated environment

## Slide 18: Formula driven Estimation
Least Accurate
Based on Statistically derived Averages
Must be Adjusted to Reflect Anticipated Environment

## Slide 19: Analogous - Estimation
Also called ‘Top-Down Estimation’
Uses the actual duration of a previous similar activity as the basis
Frequently used when limited amount of detailed information is available.
One form of Expert Judgment
More reliable when activities compared are identical
More reliable when the individual preparing the estimate has the experience of similar activities

## Slide 20: Simulation
- Uses a representation / model of a system to analyze the behavior of the system
- Involves calculating multiple duration with different sets of assumptions
- Should be used for estimation of large system
E.g.: MONTE CARLO ANALYSIS
- A distribution of probable results is defined for each activity and used to calculate a distribution of probable results for the total project
- Most commonly used simulation for large or complex projects

## Slide 21: Types of estimates & their accuracy
Order of Estimate (-25% , +75%)
An appropriate estimate made without detailed data. This type of estimate is used during the formative stages of an expenditure program for initial evaluation of the project.
Budget Estimate (-10%, +25%)
A budget estimate is prepared from flow sheets, layouts and equipment details These estimates establish the funds required and are used for obtaining approval for the project .
Definitive Estimate (-5%, +10%)
A definitive estimate is prepared from well defined data, specifications,drawings etc. This category covers all estimate ranges from a minimum to a maximum definitive type.These estimates are used for bid proposals,bid evaluations, contract changes, extra work, legal claims, permit and government approvals.

## Slide 22: Schedule Development
Input process
Project Network Diagram
Activity duration
Resource Requirement
Resource pool description
Calendars
Constraints
Assumptions
Leads and Lags
Project schedule
Supporting detail
Schedule Management plan
Resource requirement updates
Mathematical Analysis
Duration Compression
Simulation
Resource leveling
Project Management Software
Output process
Tool

## Slide 23: Shortening the Schedule
Crashing : Adding more resources to the critical path.
  Almost always results in increased cost.
  However crashing could also mean moving resources around within the project (no cost impact)
Fast Tracking : Doing more tasks in parallel.
  Results in re-work
  Increases risk
  Requires more attention to communications

## Slide 24: Schedule Control
Input process
Project schedule
Performance reports
Change requests
Schedule Management
Plan
Schedule update
Corrective actions
Lessons learned
Schedule change control
system
Performance measurement
Additional Planning
Project Management S/W
Output process
Tool

## Slide 25: More Definitions
Resource Leveling
Leveling peaks & valleys of resource use from one month to another
SPI
Ratio of work Performed to Work Scheduled
Schedule Variance
Difference between scheduled completion and actual completion
BCWP - BCWS