## Slide 1: Cost Management

## Slide 2: Cost and Management
Total Number of Units in terms of Work (Like 4 Tasks)
Total Units Of time (4 Units like 4 Days)
$ spending on 4 units of work ($4000)
Cost on those 4 units of Work.
MANAGEMENT:
You can spend $1000/day/unit of work.
EVM: Earned Value Management

## Slide 3
1 Task Estimated to 480 Man Hours.
480/8 60 Man days.
Break the major Task into 4 independent Tasks.
60/4 = 15 mandays per person.
15 Mandays + 4 Week end das = 19 Calendar days per person
If I start a 480 man hours task with 4 independent developers I can complete the task in 19 calendar days.

## Slide 4
Project Manager : $2000 / man day
Sr. Developer : $1800 / manday
Developer: $1500 / manday
Programmer: $1000 / Manday
Software Engineer: $1500 / manday
$2000+$1800+$15000+$1000 = $6300/manday
19 mandays x $6300 = 119,700

## Slide 5: Estimate a Task
Tasks can be estimated based on the following.
1. Task estimation based on the time in terms of Man days or Man hours
2. Task estimation based on the comparison with the similar task previously done based on your knowledge or experience (Expert Judgement).
3. Task estimation based on the company’s experience (Previous similar project – Historical Information), and convert the cost to current value.

## Slide 6: 1. Task estimation based on the time in terms of Man days or Man hours
LOC  (Lines Of Code)  Technic to estimate the cost of the Development Tasks.
Task is Data Conversions.
  Estimate the source data
    100 GB of MS SQL data  5 man days x $30 = $150
    100 GB of MS Access data  3 man days x $30 = $90
    100 GB of Text data  2 man days. $60
  Estimate the destination data
    50 GB of Oracle Data from MS SQL  1 man day $60
    50 GB of Oracle data from Access.  1 Man Day $60
    10 GB of Oracle data from the text.  1 Man day $60

## Slide 7
  Covert using the SQL loader
    Code to convert 100 GB of MS SQL data to Oracle Data
      20 Class developing each class with estimated 150 lines
        Logic 30 lines  30 x $2 = $60
        Data Structures 40 lines  40 x $5 = $200
        Declarations 20 lines (Constructors included) 20 $1 = $20
        Indentation 10 lines  10 x $1 = $10
        Re-structure to the destination format  50 lines
          Unit testing
            10 Scenarios x 15 LOC = 150 LOC x $5 = $750
          System testing  $250
          Testing after converting to the destination format.  $500
          QA  $1000
  Copy to the Destination Server.  $2000

## Slide 8: Agenda
Introduction
Definitions
Cost management processes
  Inputs, Tools & techniques and Outputs
Wrap up

## Slide 9: Cost Management
Project Cost Management is primarily concerned with the cost of the resources that are needed to complete the project activities.
Should also consider the ‘life-cycle cost’ before making decisions.
  Effect of Reviews on project cost Vs Lowered Maintenance costs
Prediction and Analysis of Project’s Product (Optional)
  Helps to make a ‘Go or No-Go’ decision
  Return on Investment
  Payback Analysis
Controllable and Uncontrollable Costs

## Slide 10: Why do we need Cost Management?
To complete the Project within Budget
To implement a reward and recognition system

## Slide 11: Definitions
Actual Cost
Actual Cost of Work Performed
Budget at Completion (BAC)
Budgeted Cost of Work Performed (BCWP) or Earned Value
Budgeted Cost of Work Scheduled (BCWS) or Planned Value
Cost Performance Index (CPI)
Cost Variance (CV)
Earned Value Management
Estimate at Complete (EAC)
Estimate to Complete (ETC)
Life-Cycle Costing
Parametric Estimation
S-Curve
Schedule Performance Index (SPI)
Schedule Variance (SV)

## Slide 12: Cost Management Processes
Includes the processes that are need to ensure that the project is within Budget
  Resource Planning
  Determining what resources (people, equipment and material) and in what quantities are required to complete the project
  Cost Estimating
  Developing an approximation (estimate) the cost of resources that are required to complete the project
  Cost Budgeting
  Allocating the overall cost estimate to individual work activities
  Cost Control
  Controlling the changes to the project budget

## Slide 13: Resource Planning
Inputs
  Work Breakdown Structure
  Historical Information
  Scope Statement
  Resource Pool Description
  Organizational Policies
  Activity Duration Estimates
Tools and Techniques
  Expert Judgment
  Alternatives Identification
  Project Management Software
Outputs
  Resource Requirements

## Slide 14: Resource Planning …
Resource Pool Description
  Knowledge of resource availability is a key input
  The level of detail and specificity of the RPD will vary
    At the beginning of the project, we need Programmers
    During Implementation we need some one who worked in the development phase
Organizational Policies
  The recruitment and staffing policy, Purchasing Policy must be considered during Resource Planning

## Slide 15: Resource Planning… Exercise
Describe the activities that are involved in Resource Planning
Human resources
Project Technical Resources (Proj Team)
Project Non Technical Resources
HR Managers / Admisistrators
Electronic gadgets
Laptops
Computers
Servers (H/W)
Licenses
Development Space with all utilities
Network and Internet related Setup.
Office Materials and Printers.
Technologies: (S/W)
All the licenses for technologies purchase and Maintenance

## Slide 16: Resource Planning… Exercise
Some Answers
  Identify available resources
  Review historical information about the use of resources
  Review organizational policies on resource use
  Use expert judgment on what resources are needed and available
  Quantify resource requirement by task and types of skills
  Develop Role Based Training
  Prepare a staffing management plan
  Develop a responsibility Matrix

## Slide 17: Cost Estimating
Inputs
  Work Breakdown Structure
  Resource Requirements
  Resource Rates
  Activity Duration Estimates
  Estimating Publications
  Historical Information
  Chart of Accounts
  Risks

## Slide 18: Cost Estimating …
Tools & Techniques
  Analogous Estimating
  Parametric Estimating
  Bottom-up Estimating
  Computerized tools
  Other Cost Estimating Methods
Outputs
  Cost Estimates
  Supporting Detail
  Cost Management plan

## Slide 19: Cost Estimating …
Analogous Estimating
  Estimates based on Expert judgment
  Based on similar and/or past project experiences
Bottom up Estimating
  Done by people doing the actual work
  Based on the WBS
Parametric Estimating
  Uses a mathematical model to predict costs (ex LOC, FP, Rs/Sft)
  Two types of Parametric Estimating
    Regression Analysis
    Learning Curve (a person is more productive after n weeks in the same project)

## Slide 20: Cost Estimating …Exercise
Discuss the Advantages and disadvantages of Analogous and Bottom up Estimating

## Slide 21: Cost Estimating …Exercise
Analogous
  Less expensive to estimate (estimation process itself is not time consuming)
  Quick but less accurate
  Tasks need not be identified in detail (limited detail information is available)
  Overall project costs will be capped
  Difficult for projects with uncertainty
  Requires considerable experience

## Slide 22: Cost Estimating …Exercise
Bottom-up
  More expensive to estimate (estimation process itself is time consuming)
  Elaborate and accurate
  Tasks need to be identified in detail
  Gains buy-in from the project team
  Tendency to pad the estimates
  Provides a basis for monitoring and control

## Slide 23: Accuracy of Estimates
Order of Magnitude of Estimates
  Done during the initiation phase
  Range is –25% to +75% from Actual
Budget Estimate
  Done during the planning phase
  Range is –10% to +25% from Actual
Definitive Estimate
  Done during the planning phase
  Range is –5% to +10% from Actual

## Slide 24: Cost Budgeting
Inputs
  Cost Estimates
  Work Breakdown Structure
  Project Schedule
  Risk Management Plan
Tools & Techniques
  Cost Budgeting tools and techniques
Outputs
  Cost Baseline

## Slide 25: Cost Control
Inputs
  Cost Baseline
  Performance Reports
  Change Requests
  Cost Management Plan
Tools & Techniques
  Cost Change Control System
  Performance Measurement
  Earned Value Management (EVM)
  Additional Planning
  Computerized Tools

## Slide 26: Cost Control…
Outputs
  Revised Cost Estimates
  Budget Updates
  Corrective Action
  Estimate at Completion
  Project Close out
  Lessons Learned

## Slide 27: Earned Value Management
  Actual Cost of Work Performed (AC)
    What is the actual cost incurred?
  Budgeted Cost of Work Performed (BCWP) or Earned Value (EV)
    What is the estimated value of the work actually accomplished?
  Budgeted Cost of Work Scheduled (BCWS) or Planned Value (PV)
    What is the estimated value of the work planned to be done?
  Budget at Completion (BAC)
    How much did you BUDGET for the total Job?
  Estimate at Complete (EAC)
    What do we currently expect the TOTAL project to cost?
  Estimate to Complete (ETC)
    From now on, how much MORE do we expect it to cost to finish the project?
  Variance at Completion
    How much over or under budget do we expect it to be?

## Slide 28: Earned Value Management .. Formulae
Cost Variance (CV) = EV – AC
  Negative is over budget and +ve is under budget
Schedule Variance (SV) = EV – PV
  +ve is ahead of schedule and –ve is behind schedule
Cost Performance Index (CPI) = EV/AC
Schedule Performance Index (SPI) = EV/PV
Estimate At Complete (EAC) = BAC/CPI
Estimate To Complete (ETC) = EAC – AC
Variance At Completion (VAC) = BAC - EAC

## Slide 29: Earned Value Management – Exercise
You have to build a system with 4 screens. Assume that each screen takes one day and costs $1000 to build. They are to be done one after the other. Today is end of day three.
Using the project status chart below, and answer the questions on the next slide. Also interpret the answers.
200
200
600

## Slide 30: Earned Value Management - Exercise

## Slide 31: Earned Value Management - Exercise

## Slide 32: Other Terms
  PV = FV / (1 + r)n
  PV = Present Value
  FV = Future Value
  r = interest rate
  n = number of time periods
  What is the present value of US $150,000 received three years from now if the interest rate is expected to be 10%?

## Slide 33: Answer
PV = 150000 (1 + 0.1)3
PV of 150,000 is 150000/1.331 or 112,697.

## Slide 34: More Terminology
Net Present Value
  Total Benefits less the costs
  You have two projects to choose from. A will take 3 years to complete and has a NPV of 45,000 and B will take 5 years to complete and has a NPV of 75,000. Which one would you choose?
Internal Rate of Return (IRR)
  The rate at which the revenues and costs are equal.
Pay Back Period
Benefit Cost Ratio (BCR)
Opportunity Cost
Law of Diminishing Returns
Notes: NPV – Answer is B; No of years does not matter. NPV has taken that into account.

## Slide 35: More Terminology
Sunk Costs
  A project that was originally estimated to cost 1 million. It is now half way done, and $ 2 M has been spent already. Now the committee has to decide whether to continue the project or not. Should they consider the fact that $2M has been spent already?
  No; Sunk Costs should never be considered for such a decision
Working Capital
Project Selection Methods (PV, NPV, IRR, Payback Period, Benefit Cost Ratio)
Depreciation
  Straight Line depreciation
  Accelerated depreciation
Value Analysis

## Slide 36: Thank you Q & A