## Slide 1: Cost Management

## Slide 2: Agenda
Introduction
Definitions
Cost management processes
  Inputs, Tools & techniques and Outputs
Wrap up

## Slide 3: Cost Management
Project Cost Management is primarily concerned with the cost of the resources that are needed to complete the project activities.
Should also consider the ‘life-cycle cost’ before making decisions.
  Effect of Reviews on project cost Vs Lowered Maintenance costs
Prediction and Analysis of Project’s Product (Optional)
  Helps to make a ‘Go or No-Go’ decision
  Return on Investment
  Payback Analysis
Controllable and Uncontrollable Costs

## Slide 4: Why do we need Cost Management?
To complete the Project within Budget
To implement a reward and recognition system

## Slide 5: Definitions
Actual Cost
Actual Cost of Work Performed
Budget at Completion (BAC)
Budgeted Cost of Work Performed (BCWP) or Earned Value
Budgeted Cost of Work Scheduled (BCWS) or Planned Value
Cost Performance Index (CPI)
Cost Variance (CV)
Earned Value Management
Estimate at Complete (EAC)
Estimate to Complete (ETC)
Life-Cycle Costing
Parametric Estimation
S-Curve
Schedule Performance Index (SPI)
Schedule Variance (SV)

## Slide 6: Cost Management Processes
Includes the processes that are need to ensure that the project is within Budget
  Resource Planning
  Determining what resources (people, equipment and material) and in what quantities are required to complete the project
  Cost Estimating
  Developing an approximation (estimate) the cost of resources that are required to complete the project
  Cost Budgeting
  Allocating the overall cost estimate to individual work activities
  Cost Control
  Controlling the changes to the project budget

## Slide 7: Resource Planning
Inputs
  Work Breakdown Structure
  Historical Information
  Scope Statement
  Resource Pool Description
  Organizational Policies
  Activity Duration Estimates
Tools and Techniques
  Expert Judgment
  Alternatives Identification
  Project Management Software
Outputs
  Resource Requirements

## Slide 8: Resource Planning …
Resource Pool Description
  Knowledge of resource availability is a key input
  The level of detail and specificity of the RPD will vary
    At the beginning of the project, we need Programmers
    During Implementation we need some one who worked in the development phase
Organizational Policies
  The recruitment and staffing policy, Purchasing Policy must be considered during Resource Planning

## Slide 9: Resource Planning… Exercise
Describe the activities that are involved in Resource Planning

## Slide 10: Resource Planning… Exercise
Some Answers
  Identify available resources
  Review historical information about the use of resources
  Review organizational policies on resource use
  Use expert judgment on what resources are needed and available
  Quantify resource requirement by task and types of skills
  Develop Role Based Training
  Prepare a staffing management plan
  Develop a responsibility Matrix

## Slide 11: Cost Estimating
Inputs
  Work Breakdown Structure
  Resource Requirements
  Resource Rates
  Activity Duration Estimates
  Estimating Publications
  Historical Information
  Chart of Accounts
  Risks

## Slide 12: Cost Estimating …
Tools & Techniques
  Analogous Estimating
  Parametric Estimating
  Bottom-up Estimating
  Computerized tools
  Other Cost Estimating Methods
Outputs
  Cost Estimates
  Supporting Detail
  Cost Management plan

## Slide 13: Cost Estimating …
Analogous Estimating
  Estimates based on Expert judgment
  Based on similar and/or past project experiences
Bottom up Estimating
  Done by people doing the actual work
  Based on the WBS
Parametric Estimating
  Uses a mathematical model to predict costs (ex LOC, FP, Rs/Sft)
  Two types of Parametric Estimating
    Regression Analysis
    Learning Curve (a person is more productive after n weeks in the same project)

## Slide 14: Cost Estimating …Exercise
Discuss the Advantages and disadvantages of Analogous and Bottom up Estimating

## Slide 15: Cost Estimating …Exercise
Analogous
  Less expensive to estimate (estimation process itself is not time consuming)
  Quick but less accurate
  Tasks need not be identified in detail (limited detail information is available)
  Overall project costs will be capped
  Difficult for projects with uncertainty
  Requires considerable experience

## Slide 16: Cost Estimating …Exercise
Bottom-up
  More expensive to estimate (estimation process itself is time consuming)
  Elaborate and accurate
  Tasks need to be identified in detail
  Gains buy-in from the project team
  Tendency to pad the estimates
  Provides a basis for monitoring and control

## Slide 17: Accuracy of Estimates
Order of Magnitude of Estimates
  Done during the initiation phase
  Range is –25% to +75% from Actual
Budget Estimate
  Done during the planning phase
  Range is –10% to +25% from Actual
Definitive Estimate
  Done during the planning phase
  Range is –5% to +10% from Actual

## Slide 18: Cost Budgeting
Inputs
  Cost Estimates
  Work Breakdown Structure
  Project Schedule
  Risk Management Plan
Tools & Techniques
  Cost Budgeting tools and techniques
Outputs
  Cost Baseline

## Slide 19: Cost Control
Inputs
  Cost Baseline
  Performance Reports
  Change Requests
  Cost Management Plan
Tools & Techniques
  Cost Change Control System
  Performance Measurement
  Earned Value Management (EVM)
  Additional Planning
  Computerized Tools

## Slide 20: Cost Control…
Outputs
  Revised Cost Estimates
  Budget Updates
  Corrective Action
  Estimate at Completion
  Project Close out
  Lessons Learned

## Slide 21: Earned Value Management
  Actual Cost of Work Performed (AC)
    What is the actual cost incurred?
  Budgeted Cost of Work Performed (BCWP) or Earned Value (EV)
    What is the estimated value of the work actually accomplished?
  Budgeted Cost of Work Scheduled (BCWS) or Planned Value (PV)
    What is the estimated value of the work planned to be done?
  Budget at Completion (BAC)
    How much did you BUDGET for the total Job?
  Estimate at Complete (EAC)
    What do we currently expect the TOTAL project to cost?
  Estimate to Complete (ETC)
    From now on, how much MORE do we expect it to cost to finish the project?
  Variance at Completion
    How much over or under budget do we expect it to be?

## Slide 22: Earned Value Management .. Formulae
Cost Variance (CV) = EV – AC
  Negative is over budget and +ve is under budget
Schedule Variance (SV) = EV – PV
  +ve is ahead of schedule and –ve is behind schedule
Cost Performance Index (CPI) = EV/AC
Schedule Performance Index (SPI) = EV/PV
Estimate At Complete (EAC) = BAC/CPI
Estimate To Complete (ETC) = EAC – AC
Variance At Completion (VAC) = BAC - EAC

## Slide 23: Earned Value Management – Exercise
You have to build a system with 4 screens. Assume that each screen takes one day and costs $1000 to build. They are do be done one after the other. Today is end of day three.
Using the project status chart below, and answer the questions on the next slide. Also interpret the answers.

## Slide 24: Earned Value Management - Exercise

## Slide 25: Earned Value Management - Exercise

## Slide 26: Other Terms
  PV = FV / (1 + r)n
  PV = Present Value
  FV = Future Value
  r = interest rate
  n = number of time periods
  What is the present value of US $150,000 received three years from now if the interest rate is expected to be 10%?

## Slide 27: Answer
PV = 150000 (1 + 0.1)3
PV of 150,000 is 150000/1.331 or 112,697.

## Slide 28: More Terminology
Net Present Value
  Total Benefits less the costs
  You have two projects to choose from. A will take 3 years to complete and has a NPV of 45,000 and B will take 5 years to complete and has a NPV of 75,000. Which one would you choose?
Internal Rate of Return (IRR)
  The rate at which the revenues and costs are equal.
Pay Back Period
Benefit Cost Ratio (BCR)
Opportunity Cost
Law of Diminishing Returns
Notes: NPV – Answer is B; No of years does not matter. NPV has taken that into account.

## Slide 29: More Terminology
Sunk Costs
  A project that was originally estimated to cost 1 million. It is now half way done, and $ 2 M has been spent already. Now the committee has to decide whether to continue the project or not. Should they consider the fact that $2M has been spent already?
  No; Sunk Costs should never be considered for such a decision
Working Capital
Project Selection Methods (PV, NPV, IRR, Payback Period, Benefit Cost Ratio)
Depreciation
  Straight Line depreciation
  Accelerated depreciation
Value Analysis

## Slide 30: Thank you Q & A