## Slide 1: Communication Management

## Slide 2: Contents
Introduction
Communication management processes
  Inputs, Tools & techniques and Outputs
Wrap up

## Slide 3: Communication Management
Communication Management includes the processes required to generate, collect, disseminate, store and ultimately dispose project information.
Involves all the stake holders of the project
It is NOT “Communication Skills” as we generally perceive

## Slide 4: Why do we need Communication Management?

## Slide 5: Communication Management Processes
  Communications Planning
  Determining the information and communications needs of the stakeholders; Who needs what information, When they will need it and how it should be given
  Information Distribution
  Making needed information available to project stakeholders in a timely manner
  Performance Reporting
  Collecting and disseminating performance information, including status reports, progress measurement and forecasting
  Administrative Closure
  Generating, gathering and disseminating information to formalize a phase or project completion

## Slide 6: Communications Management
Each of the processes occur at least once in a project
They interact with each other and with the processes in other knowledge areas as well

## Slide 7: Communications Planning
Inputs
  Communications Requirements
  Communications Technology
  Constraints
  Assumptions
Tools and Techniques
  Stakeholder Analysis
Outputs
  Communications Management Plan

## Slide 8: Communications Planning
  Overview
    Proactively determining the information needs of the stake holders
    Who needs the information, when and in What form?
    Organizational structure will have a major say
    Communication Media include face-to-face, e-mail, meetings, telephone, fax etc
    The PM spends about 90% of the time communicating
    Care should be taken to avoid wasting resources on unnecessary information or inappropriate technology

## Slide 9: Communications Management Plan
Output of Communications Planning
Includes
  What information needs to be collected and when
  Who will receive the information
  Methods used to gather and store information
  Limits, if any, on who may give direction and to whom
  Reporting Relationships
  List of contact information of all stakeholders
  Schedule for distribution of information

## Slide 10: Exercise
What information needs to be distributed on a project?

## Slide 11: Information Distribution
Inputs
  Work Results
  Communications Management Plan
  Project Plan
Tools & Techniques
  Communication skills
  Information Retrieval systems (e-cockpit?)
  Information distribution methods
Outputs
  Project records
  Project outputs
  Project Presentations

## Slide 12: Communication Channels
Communications grow at non-linear rate
If there are N people, then there are N(N-1)/2 communication channels possible
Communications need to be managed but cannot be controlled

## Slide 13: Performance Reporting
Inputs
  Project Plan
  Work Results
  Other Project Records
Tools & Techniques
  Performance Reviews
  Variance, Trend, Earned Value Analysis
  Information distribution tools and techniques
Outputs
  Performance Reports
  Change Requests

## Slide 14: Exercise
Create a sample report for your project giving the status, progress and trends.
Include a distribution list

## Slide 15: Administrative Closure
Inputs
  Performance Measurement documentation
  Product documentation
  Other Project records
Tools & Techniques
  Performance reporting tools and techniques
  Project reports
  Project Presentations
Outputs
  Project Archives
  Project Closure
  Lessons Learned

## Slide 16: Administrative Closure
Collecting Records
Updating Records
Archiving Records
Documenting all correspondence
Lessons Learned
Formal Acceptance
Product Verification
Performance Reporting

## Slide 17: Communication Model
Communication has three parts; Sender, Receiver and the Message
The message is decoded by the receiver based on the receiver’s education, experience, language and culture.
Acknowledging the message (“Message understood”) helps.
About 55% of communication is Non-Verbal
Feedback is essential to reduce communication barrier (“Do you understand what I have explained?”)

## Slide 18: Communication Methods
Complex Problems, Project Plans, Project Charter, Communicating over long distances | Memos, e-mail, Notes
Presentations, Speeches | Meetings, Conversations, Teleconferences
Written
Verbal
Formal
Informal

## Slide 19: Communication Blockers
Noise
Distance
Improper en-coding of messages
Saying “that is a bad idea”
Hostility
Language
Culture

## Slide 20: Performance Reporting
Status Report – Where the project now stands
Progress Report – What has been accomplished
Trend Report – Examining project results over time to see if performance is improving or deteriorating
Forecasting – Predicting future project status
Variance Report
Earned Value Report

## Slide 21: Rules for Meetings
Set a time limit and keep to it
Schedule recurring meetings in advance
Meeting with team regularly, but not too often
Have a purpose for the meeting
Create an Agenda with team input
Distribute Agenda beforehand
Stick to the Agenda
Let people know in advance their responsibilities
Bring the right people together
Chair and lead the meeting with a set of rules
Assign deliverables and time limits for all tasks that result
Document and Publish minutes

## Slide 22: Earned Value Management
  Actual Cost of Work Performed (AC)
    What is the actual cost incurred?
  Budgeted Cost of Work Performed (BCWP) or Earned Value (EV)
    What is the estimated value of the work actually accomplished?
  Budgeted Cost of Work Scheduled (BCWS) or Planned Value (PV)
    What is the estimated value of the work planned to be done?
  Budget at Completion (BAC)
    How much did you BUDGET for the total Job?
  Estimate at Complete (EAC)
    What do we currently expect the TOTAL project to cost?
  Estimate to Complete (ETC)
    From now on, how much MORE do we expect it to cost to finish the project?
  Variance at Completion
    How much over or under budget do we expect it to be?

## Slide 23: Earned Value Management .. Formulae
Cost Variance (CV) = EV – AC
  Negative is over budget and +ve is under budget
Schedule Variance (SV) = EV – PV
  +ve is ahead of schedule and –ve is behind schedule
Cost Performance Index (CPI) = EV/AC
Schedule Performance Index (SPI) = EV/PV
Estimate At Complete (EAC) = BAC/CPI
Estimate To Complete (ETC) = EAC – AC
Variance At Completion (VAC) = BAC - EAC

## Slide 24: Earned Value and Microsoft Project

## Slide 25: Earned Value in MS-Project

## Slide 26: Earned Value Graphs using MS-Project

## Slide 27: Exit Quiz
Please answer the questions in the Quiz and submit the sheet in 30 minutes.

## Slide 28: Thank you !!!