## Risk Identification & Analysis
Risk Identification, Analysis and Mitigation |  | Back End Team | Anteneh, Meron, Jimmy, Xuan, Daniel
Team Anteneh |  | Front End Team | Amit, Haftu, Christian, Dinh
Risk Category/Questions for Consideration | Identified Risks | Risk Owner | Risk Likelihood ( Out of 10) | Risk Severity ( Out of 10) | Risk Ranking | Mitigation
1) Scope Risks
Shopping Cart Module | a) Risk of not able to combine all the functionalities of the shopping cart like edit product, checkout etc. | Christian and Xuan | 3 | 3 | 7 | Focus on making components work together one by one
Product Module | b) Implementing filters in the product list homepage | Amit and Jimmy | 7 | 6 | 17 | Research more on front end filters
Payment Module | c) Combining all the modules with Payment module | Daniel and Haftu | 6 | 6 | 6 | Look at some sample projects that implement their own payment module
Payment Module | d) Address validation since we wont be using any maps api to verify addresses entered by user | Daniel and Haftu | 8 | 2 | 18 | If time allows, research and use address validation apis
Report Module | e) team members do not have experience with jasper/CR | Meron | 7 | 7 | 8 | Starter with simpler reports and build on it to make it more complex
Front End Module | f) Exposing reports data to front end because no experience with it | Meron, Amit, Haftu, Christian, Dinh | 6 | 6 | 9 | Research on how to display reports using React
2) Technical Risks
| a) For the front end, the developers might not be able to use all the functionalities of React because of inexperience. | Front End Team | 6 | 5 | 2 | Research best practices and start from functionalities you know about. If efficient ways are found, incorporate it later
| b) Developers do not apply the correct Design Patterns and algorithms (Strategy pattern for Payment Module) | Back End Team | 3 | 2 | 15 | Research on Design Patterns that can be used with Spring
| c) Developers work in technology and tools that are not the best | Whole Team | 3 | 2 | 16 | Establish best practices and development environment before starting to code
| d) Developers do not develop Unit Test for each class | Back End Team | 5 | 5 | 3 | Follow TDD
| f) Developers do not follow the best coding practices | Whole Team | 3 | 2 | 4 | Enforce Best Practices for maximum code readiness and test potential
| e) Developers do not use CI/CD to improve the process of development | Whole Team | 3 | 2 | 10 | Use GIT and Jenkins/or CircleCI
3) External Predictable Risks
| a) The environment (database, server) is not the same in Production (Professor computer) and Development (Team member computers) | Whole Team | 5 | 5 | 11 | Can deploy to Heroku or use docker
| 2) Users do not have knowlege on how to use the application | Dinh(QA) and Front End Team | 3 | 3 | 12 | Make UI intuitive and do tests with QA
4) External Unpredictable Risks
| a) A lot of requests from the users can overload the server and cause errors. | Whole Team | 2 | 2 | 10 | Use Transactional Management
| b) Because of remote work and time zone differences of team members, unsure how the project will go on | Whole Team | 6 | 7 | 1 | Communicate frequently and update Trello
5) Quality Risks
| a) The Unit test do not cover all the application | Back End Team | 6 | 6 | 5 | Test each functionalities immediately after coding
| b) Developers do not use automated tools for quality code | Whole Team | 3 | 3 | 14 | Establish automated tools early on
6) Legal Risks
| a) Copyright issues | Whole Team | 2 | 2 | 13 | Use free and open source project materials