## Risk Identification & Analysis
Risk Identification, Analysis and Mitigation |  | Back End Team | Anteneh, Meron, Jimmy, Xuan, Daniel
Team Anteneh |  | Front End Team | Amit, Haftu, Christian, Dinh
Risk Category/Questions for Consideration | Identified Risks | Risk Owner | Risk Likelihood ( Out of 10) | Risk Severity ( Out of 10) | Risk Ranking | Mitigation | Risk Response Strategy
1) Scope Risks
Shopping Cart Module | a) Risk of not able to combine all the functionalities of the shopping cart like edit product, checkout etc. | Christian and Xuan | 3 | 3 | 7 | Focus on making components work together one by one | Christian and Xuan will collaborate and establish proper workflow to integrate all the submodules for the shopping cart modules to avoid conflicts
Product Module | b) Implementing filters in the product list homepage | Amit and Jimmy | 7 | 6 | 17 | Research more on front end filters | Subtasks under Search Products submodules such as Search by ID and Search by Price was removed
Payment Module | c) Combining all the modules with Payment module | Daniel and Haftu | 6 | 6 | 6 | Look at some sample projects that implement their own payment module | Online Training is required for the Daniel and Haftu to successfully integrate Payment module into the app. Back end team will routinely communicate with all the members to prevent conflicts
Payment Module | d) Address validation since we wont be using any maps api to verify addresses entered by user | Daniel and Haftu | 8 | 2 | 18 | If time allows, research and use address validation apis | No experience using Maps API to validate addresses so removing this resource from the project
Report Module | e) team members do not have experience with jasper/CR | Meron | 7 | 7 | 8 | Starter with simpler reports and build on it to make it more complex. | Meron will be self-training herself with online tutorials to get acquainted with Jasper
Front End Module | f) Exposing reports data to front end because no experience with it | Meron, Amit, Haftu, Christian, Dinh | 6 | 6 | 9 | Research on how to display reports using React | Front End team will be self-training with online tutorials to get acquainted with dispalying reports
2) Technical Risks
| a) For the front end, the developers might not be able to use all the functionalities of React because of inexperience. | Front End Team | 6 | 5 | 2 | Research best practices and start from functionalities you know about. If efficient ways are found, incorporate it later | Front end developers might not be able to use all the functionalities of React because of inexperience. Provide Amit, Chritian, Dinh, Haftu with additional online training
| b) Developers do not apply the correct Design Patterns and algorithms (Strategy pattern for Payment Module) | Back End Team | 3 | 2 | 15 | Research on Design Patterns that can be used with Spring | All team members will agree on select design patterns and follow that throughout the completion of project
| c) Developers work in technology and tools that are not the best | Whole Team | 3 | 2 | 16 | Establish best practices and development environment before starting to code | Jimmy will suggesting best tools on back-end and Amit on the front end. The team will follow the enforced practices unless the whole team decides otherwise
| d) Developers do not test their codes | Back End Team | 5 | 5 | 3 | Follow TDD | Revert to guidelines on TDD and self-train
| f) Developers do not follow the best coding practices | Whole Team | 3 | 2 | 4 | Enforce Best Practices for maximum code readiness and test potential | Already Covered
| e) Developers do not use CI/CD to improve the process of development | Whole Team | 3 | 2 | 10 | Use GIT and Jenkins/or CircleCI | Self-train Amit, Christian, Ho, Haftu on CircleCI for frontend
3) External Predictable Risks
| a) The environment (database, server) is not the same in Production (Professor computer) and Development (Team member computers) | Whole Team | 5 | 5 | 11 | Can deploy to Heroku or use docker | Remove and replace risk task associated with using Heroku if risk is not mitigated
| 2) Users do not have knowlege on how to use the application | Dinh(QA) and Front End Team | 3 | 3 | 12 | Make UI intuitive and do tests with QA | Dinh as a QA and the front end team can be involved in continuous feeback loop on UI
4) External Unpredictable Risks
| a) A lot of requests from the users can overload the server and cause errors. | Whole Team | 2 | 2 | 10 | Use Transactional Management | Can use Actuator for monitoring transaction volumes
| b) Because of remote work and time zone differences of team members, unsure how the project will go on | Whole Team | 6 | 7 | 1 | Communicate frequently and update Trello | Use agreed timezone to avoid conflicts between team members
5) Quality Risks
| a) The Unit test do not cover all the application | Back End Team | 6 | 6 | 5 | Test each functionalities immediately after coding | Revert to guidelines on TDD and self-train
| b) Developers do not use automated tools for quality code | Whole Team | 3 | 3 | 14 | Establish automated tools early on | Self-train Amit, Christian, Ho, Haftu on CircleCI for frontend
6) Legal Risks
| a) Copyright issues | Whole Team | 2 | 2 | 13 | Use free and open source project materials | Agree on open source codes and tools the team needs to use
Note on B4: Input SPECIFIC risks that your team identifies when discussing questions for consideration.
Note on D4: Likelihood of Risk Occurring 4 = Very Likely – Almost certain to occur over the life of the project (or a 10 year period, whichever is shorter) 3 = Likely – Probably will occur during a 10-year period 2 = Unlikely – Probably will NOT occur during a 10-year period 1 = Very Unlikely – Almost certain NOT to occur during a 10-year period
Note on E4: Severity of Risk 4 = Very High – Would prevent goals and objectives from being achieved 3 = High – Would cause significant problems or delays in objectives being achieved 2 = Medium – Would cause relatively minor problems or delays in objectives being achieved 1 = Low – Would probably not affect project implementation